## Slide 1: 2017 CASE Circle of Excellence
Rice University

## Slide 2: Table of Contents
Planning Slide 3
Outreach Slide 7
Email Slide 16
Web Slide 27
Events Slide 34

## Slide 3: Planning

## Slide 4: CREATIVE WORK PLAN
PROJECT OVERVIEW:
For the gala weekend, the signature experience will be the gala, but all events and programs happening that weekend will also be marketed to promote attendance and participation throughout the weekend. There will be a robust communications roll out that will include a call for nominations/save the date, printed invitations approximately 8 weeks in advance, email invitations, paid and promoted social media posts, and event collateral design such as slides, videos, banners, and the awards themselves for the honorees. In addition to ARUBA specific emails and marketing, the weekend will be promoted in Houston and all-alumni newsletters leading up to the event to build awareness and encourage participation among the greater Rice alumni and friends community.
PROJECT GOALS:
  Reengage alumni, plug into Rice
  Endowment legacy
  Inclusive of faculty, including new faculty
  Connect with students, opportunity for them to connect with alumni
  Celebrate from where we came and where we are going
  Create an archive for milestones

## Slide 5: KEY COMMUNICATIONS DATES: June 16 Website Phase I June 24 RFP for Gala Video(s) Complete June 22 Email 1 of 5 July 11 Commission Update Email July 15 All Alumni Newsletter July 18 Campus Email Aug 5 Website Phase II Aug 8 Print Invitation Drops in Mail Aug 8 Volunteer Outreach Toolkit Ready Aug 10-11 Email 2 of 5 Aug 12 DC & NYC Regional Emails Aug 19 Bay Area Regional Email Aug 26 Houston Events Digest Aug 29-Sept 2 Website Phase III Sept 2 Austin & Dallas Regional Emails Sept 5 Email 3 of 5 Sept 5-12 Rice News Sept 23 Email 4 of 5 Sept 28 Event Program Delivered Sept 28 Final Video(s) Delivered Sept 30 Houston Events Digest Sept 30-Oct 2 ARUBA Reunion Weekend 2016 Oct 7 Email 5 of 5

## Slide 6
DELIVERABLE | PURPOSE/TASK | SEGMENT | DEADLINE | NOTES
Email 1 of 5 | Save the date for gala; nominations open; recap of year-to-date | ARUBA; Commission | June 22 | 
All Alumni Newsletter | Save the date; nominate | All | July 8-15 | Reminder to nominate
Campus email | Nominate | All-Depts | July 18 | 
Email 2 of 5 | Email invitation w/ link to registration page | ARUBA, Commission | August 10-11 | Send shortly after print invitation drops
DC & NYC regional emails | Blurb announcing registration is open | DC & NYC alums | August 12 | 
Commission update | Announce winners prior to broader announcement | Volunteers | TBD | 
Bay Area regional email | Blurb announcing registration is open | Bay Area alums | Aug. 19 | 
Commission update email | Reminder to nominate; save the date | Commission | July 11 Mid-late August | Per Dan 6/27: The commission update can go in mid-late August as a “kickoff to the fall” type of message
Houston event digest | Highlight gala as a signature event | Houston alumni | Aug. 26 | 
Austin and Dallas regional emails | Blurb announcing registration is open | Austin and Dallas alums | Sept. 2 | 
Email 3 of 5 | Announce award-winners and link to registration | ARUBA, Commission, Others TBD | September 5 | Highlight award winners with brief bios; 2nd reminder to register
Rice News | Announcement of award winners | Subscribers | September 5-12 | 
Email 4 of 5 | Last chance to register | ARUBA, Commission, Others TBD, minus registrants | September 23 | Last chance: approx. one week out of event
Houston event digest | Reminder for weekend; walkups accepted (TBD) | Houston alumni | September 30 | 
Email 5 of 5 | Thank you and survey | Attendants of gala | Oct. 7 | Include any notes about remaining events for 50 year celebration; link to photos

## Slide 7: Student and Community Outreach

## Slide 14: RICE MAGAZINE, FALL 2016 HTTPS://ISSUU.COM/RICEUNIVERSITY/DOCS/FALL2016RICEMAG_ISSUU

## Slide 16: Email

## Slide 17
ARUBA 50 Years Celebration
Email 1 of 3

## Slide 18
ARUBA 50 Years Celebration
Email 2 of 3

## Slide 19
ARUBA 50 Years Celebration
Email 3 of 3

## Slide 20
ARUBA 50 Years Athletics
Emails 1 to 3

## Slide 21
ARUBA Gala
Email 1 of 5

## Slide 22
ARUBA Gala
Email 2 of 5

## Slide 23
ARUBA Gala
Email 3 of 5

## Slide 24
ARUBA Gala
4 of 5

## Slide 25
ARUBA Gala
Registrant Email

## Slide 26
ARUBA Gala
5 of 5

## Slide 27: Web

## Slide 28: CELEBRATING 50 YEARS OF BLACK UNDERGRADUATE LIFE HTTP://ALUMNI.RICE.EDU/EVENTS/50-YEARS-OF-BLACK-UNDERGRADUATE-LIFE

## Slide 29: ARUBA HTTP://ALUMNI.RICE.EDU/ARUBA

## Slide 30: VIDEO: CELEBRATING 50 YEARS HTTP://ALUMNI.RICE.EDU/EVENTS/50-YEARS-OF-BLACK-UNDERGRADUATE-LIFE/VIDEO-CELEBRATING-50-YEARS-OF-BLACK-UNDERGRADUATE-LIFE-AT-RICE

## Slide 31: ARUBA LEGACY ENDOWMENT HTTP://ALUMNI.RICE.EDU/EVENTS/50-YEARS-OF-BLACK-UNDERGRADUATE-LIFE/LEGACY-ENDOWMENT

## Slide 32: BLACK HISTORY AT RICE TIMELINE HTTP://ALUMNI.RICE.EDU/BLACK-HISTORY-AT-RICE-TIMELINE

## Slide 33: Web Banners

## Slide 34: Events

## Slide 35: TRAILBLAZERS IN RICE ATHLETICS PROGRAM

## Slide 36: Gala Print Invitation

## Slide 40: BLUEPRINT FOR EXCELLENCE Gala Program

## Slide 50: Gala Award

## Slide 52: EVENT PHOTOS
For more event photos, please visit:
https://www.flickr.com/photos/ricepublicaffairs/26170425361/in/album-72157666659626791
and
https://www.flickr.com/photos/ricepublicaffairs/albums/72157674732413625

## Slide 53: THANK YOU